| Chair’s Report |  |  |
| --- | --- | --- |
| Name of Committee: | Targeted Intervention Improvement Framework (TIIF) Steering Group |  |
| Meeting date: | 21.11.22 |  |
| Name of Chair: | Nick Lyons, Deputy Chief Executive / Executive Medical Director |  |
| Responsible Director: | Nick Lyons, Deputy Chief Executive / Executive Medical Director |  |
| Summary of business discussed: | - Nick Lyons has taken over from Gill Harris as Chair of the TI Steering Group following the recent change in positions. - It has been agreed to set a twelve month target for the TI self assessment scores for each domain rather than a six month target which has been previously in place. - During the meeting with Welsh Government on 10.11.22 the self assessment scores for each domain were agreed. - A TI Working Group workshop is taking place on 29.11.22 and Olivia Shorrocks from WG has agreed to join the meeting and share some key deliverables to focus on to reach level 3 and beyond. - There is a need to ensure TI is at the front and centre of the Health Board work, that we are all using the same language and that the same issues are being discussed in relevant meetings across the organisation. - The Group approved the submission of evidence received from the YGC domain to move for a level 0 to a level 1. - The Group considered and discussed an appropriate risk for the TI programme. - The Terms of Reference for the TI Working Group, TI Evidence of Outcomes Group and TI Steering Group were discussed. - The Performance maturity matrix was shared with the Group and a revised version will go to the next meeting of the Group for formal approval before being shared with WG. |  |
| Key assurances provided at this meeting: | - Governance arrangements are in place to monitor TI progress via Steering Group oversight. |  |
| Key risks including mitigating actions and milestones | - No risks were raised |  |
| TIIF Domain addressed | - All |  |
| Issues to be referred to another Committee | - The TI programme risk will be discussed at the Risk Management Group. |  |
| Matters requiring escalation to the Board: | - None |  |
| Well-being of Future Generations Act Sustainable Development Principle | Describe how the items of business and the development of any proposals considered by the Committee gave adequate consideration to the sustainable development principles or if not indicate the reasons for this. 1. Balancing short term need with long term planning for the future – covered by the strategy, planning and performance domain. 2. Working together with other partners to deliver objectives – covered by the engagement work 3. Involving those with an interest and seeking their views – covered by the engagement work; 4.Putting resources into preventing problems occurring or getting worse – via WG funding allocation; 5. Considering impact on all well-being goals together and on other bodies – covered by engagement work. |  |
| Planned business for the next meeting: | - Approval of Performance Maturity Matrix |  |
| Date of next meeting: | 19.12.22 |  |

V1.0