| Chair’s Report |  |  |
| --- | --- | --- |
| Name of Committee: | Targeted Intervention Improvement Framework (TIIF) Steering Group |  |
| Meeting date: | 04.07.22 |  |
| Name of Chair: | Gill Harris, Deputy Chief Executive / Executive Director of Integrated Clinical Delivery |  |
| Responsible Director: | Gill Harris, Deputy Chief Executive / Executive Director of Integrated Clinical Delivery |  |
| Summary of business discussed: | - The Chair made reference to the recent Welsh Government announcement of Targeted Intervention (TI) arrangements which have been extended to include a specific focus on services at Ysbyty Glan Clwyd (YGC) which will include Vascular and ED as specific services. - Welsh Government have suggested the maturity matrices are reviewed and may require rewording to reflect the additions. - The development of the maturity matrix for the YGC domain and the separation of Performance from Strategy and Planning domain is to be completed by the end of July. These will then be presented to a Board Workshop for scrutiny prior to formal presentation to the Board. - Discussions are ongoing with WG regarding the YGC element and possibly the Mental Health element as there will be an increase in focus on governance and oversight in these specific work streams. - The terms of reference for the Steering Group, Evidence Group and Outcomes Group will be reviewed to reflect the governance arrangements going forward. - An SBAR on the Performance domain was presented to formalise the agreement by WG to separate the Performance element from the Strategy and Planning element within the Strategy, Planning and Performance domain. - The group discussed the proposed changes which have been put forward for the CAMHS element of the Mental Health domain, the Engagement domain and the Strategy and Planning domain. |  |
| Key assurances provided at this meeting: | - Governance arrangements are in place to monitor TI progress via Steering Group oversight. |  |
| Key risks including mitigating actions and milestones | - No risks were raised |  |
| TIIF Domain addressed | - All |  |
| Issues to be referred to another Committee | - None |  |
| Matters requiring escalation to the Board: | - None |  |
| Well-being of Future Generations Act Sustainable Development Principle | Describe how the items of business and the development of any proposals considered by the Committee gave adequate consideration to the sustainable development principles or if not indicate the reasons for this. 1. Balancing short term need with long term planning for the future – covered by the strategy, planning and performance domain. 2. Working together with other partners to deliver objectives – covered by the engagement work 3. Involving those with an interest and seeking their views – covered by the engagement work; 4.Putting resources into preventing problems occurring or getting worse – via WG funding allocation; 5. Considering impact on all well-being goals together and on other bodies – covered by engagement work. |  |
| Planned business for the next meeting: | - This will be a sub set of the Steering Group and will concentrate on the development YGC and Performance maturity matrices. |  |
| Date of next meeting: | 18.07.22 |  |

V1.0