| Chair’s Report |  |  |
| --- | --- | --- |
| Name of Committee: | Targeted Intervention Improvement Framework (TIIF) Steering Group |  |
| Meeting date: | 22.02.22 |  |
| Name of Chair: | Gill Harris, Deputy Chief Executive / Executive Director of Integrated Clinical Delivery |  |
| Responsible Director: | Gill Harris, Deputy Chief Executive / Executive Director of Integrated Clinical Delivery |  |
| Summary of business discussed: | - Progress within each of the domains continues, as previously requested each domain provided a single slide with examples of good practice and areas of concern. - A patient story has been shared following the journey of a patient from CAMHS into MH which highlights areas of learning in terms of listening to patients, and improving services as a consequence of patient experience. A family liaison officer has now been put in post and the patient will join the Health Board as a young leader as part of the patient experience team. - Feedback was provided on the WG Oversight Meeting and specific actions have been shared within the letter received. - The Board Workshop in April will review the TI self assessment ahead of the submission deadline to Welsh Government in May 2022. - There will be an opportunity to amend the wording within the maturity matrices if required ahead of the self assessment. - The first meeting of the Evidence Group will take place in March to review and sign off the outcomes framework. |  |
| Key assurances provided at this meeting: | - Governance arrangements are in place to monitor TI progress via Steering Group oversight. - Teams are working to deliver improvements, to augment maturity levels ahead of the next self-assessment in May 2022. |  |
| Key risks including mitigating actions and milestones | - There is a risk of insufficient progress on the improvement journey; the oversight of the Steering Group and added scrutiny from IM Links will mitigate this. |  |
| TIIF Domain addressed | - All |  |
| Issues to be referred to another Committee | - None |  |
| Matters requiring escalation to the Board: | - None |  |
| Well-being of Future Generations Act Sustainable Development Principle | Describe how the items of business and the development of any proposals considered by the Committee gave adequate consideration to the sustainable development principles or if not indicate the reasons for this. 1. Balancing short term need with long term planning for the future – covered by the strategy, planning and performance domain. 2. Working together with other partners to deliver objectives – covered by the engagement work 3. Involving those with an interest and seeking their views – covered by the engagement work; 4.Putting resources into preventing problems occurring or getting worse – via WG funding allocation; 5. Considering impact on all well-being goals together and on other bodies – covered by engagement work. |  |
| Planned business for the next meeting: | - Monitoring progress against the framework and identification of any issues. |  |
| Date of next meeting: | 29.03.22 |  |