| Chair’s Report |  |  |
| --- | --- | --- |
| Name of Committee: | Targeted Intervention Improvement Framework (TIIF) Steering Group |  |
| Meeting date: | 24.10.22 |  |
| Name of Chair: | Gill Harris, Deputy Chief Executive / Executive Director of Integrated Clinical Delivery |  |
| Responsible Director: | Gill Harris, Deputy Chief Executive / Executive Director of Integrated Clinical Delivery |  |
| Summary of business discussed: | - Gill Harris highlighted that a number of Execs have not been present at recent meetings and requested this is raised at the Exec Team meeting to highlight the importance of attending the Steering Group meetings going forward. - The Steering Group conducted a final moderation of the scores proposed during the Board Workshop for each of the TI domains. Independent Members were invited to attend the Group and the table below reflects the final proposed positon ahead of the November Board report which Phil Meakin will produce. As part of the considerations it was agreed to have a stretch target by November 2023. - The principle was discussed and agreed that the target scores for November 2023 would not be a “stretch target”, rather we would seek to hit this target before November 23. It will be important to communicate this internally with TI domain colleagues and stakeholders. Domain; Score for Nov 22; Target Score for May 23; Target Score by Nov 23. All Ages Mental Health; Level 2; Level 2; Level 3. Strategy & Planning; Level 2; Level 2; Level 3. Leadership; Level 2; Level 2; Level 3. Engagement; Level 2; Level 3; Level 3. Performance; Level 1; Level 1; Level 2. YGC; Level 1; Level 2; Level 2. - The next step will be for Phil Meakin to communicate this position to the designated Link IMs and SROs for each domain. - The Performance maturity matrix will be developed to ensure the attributes better align to the outcomes. - The Steering Group agreed that there is a need to consider how the Vascular element of the YGC maturity matrix is separated from the overall matrix. - The Group received proposals for resource requirements for an effective TI programme, it was agreed that Phil Meakin and Molly Marcu would meet to discuss how to resource the TI Central Team as recommended in the paper. - It was agreed that more engagement was needed throughout the Health Board on TI to allow the organisation to demonstrate evidence of an impact on outcomes. Phil Meakin will take this work forward, this is also linked to the item above (TI Central Team) |
| Key assurances provided at this meeting: | - Governance arrangements are in place to monitor TI progress via Steering Group oversight. |  |
| Key risks including mitigating actions and milestones | - No risks were raised |  |
| TIIF Domain addressed | - All |  |
| Issues to be referred to another Committee | - Consideration of TI Resources will be discussed at the Remuneration and Terms of Service Committee. |  |
| Matters requiring escalation to the Board: | - A report will be produced by Phil Meakin for the November Board (formal self-assessment for November 20022) |  |
| Well-being of Future Generations Act Sustainable Development Principle | Describe how the items of business and the development of any proposals considered by the Committee gave adequate consideration to the sustainable development principles or if not indicate the reasons for this. 1. Balancing short term need with long term planning for the future – covered by the strategy, planning and performance domain. 2. Working together with other partners to deliver objectives – covered by the engagement work 3. Involving those with an interest and seeking their views – covered by the engagement work; 4.Putting resources into preventing problems occurring or getting worse – via WG funding allocation; 5. Considering impact on all well-being goals together and on other bodies – covered by engagement work. |  |
| Planned business for the next meeting: | - Feedback from meeting with WG 10th November - Resource for TI Central Team Update - Meeting arrangements for next 12 months |  |
| Date of next meeting: | 21.11.22 |  |

V1.0