| Chair’s Report |  |  |
| --- | --- | --- |
| Name of Committee: | Targeted Intervention Improvement Framework (TIIF) Steering Group |  |
| Meeting date: | 29.03.22 |  |
| Name of Chair: | Gill Harris, Deputy Chief Executive / Executive Director of Integrated Clinical Delivery |  |
| Responsible Director: | Gill Harris, Deputy Chief Executive / Executive Director of Integrated Clinical Delivery |  |
| Summary of business discussed: | - Amendments to TI Steering Group terms of reference were endorsed. - The Evidence Group terms of reference were discussed and it was agreed that the Associate Director of Governance will replace the Board Secretary as Vice Chair. - Each domain provided an overview of the evidence presented to the Evidence Group. - In order for the strategy, planning and performance domain to achieve a high level 2, this score is predicated on the IMTP being approved by the Board and also submitted to Welsh Government for sign off. - The suggested levels for each of the domains where highlighted as a high level 2 for all ages Mental Health, Strategy, Planning & Performance and Engagement and a level 2 for Leadership. - The Outcomes Group terms of reference were discussed and it was agreed that the Lead for Digital will replace the Executive Director of Finance as the Vice Chair. - Requested amendments to the CAMHS and Strategy, Planning & Performance maturity matrices were approved. |  |
| Key assurances provided at this meeting: | - Governance arrangements are in place to monitor TI progress via Steering Group oversight. |  |
| Key risks including mitigating actions and milestones | - There is a key risk relating to adult mental health and CAMHS that workforce and recruitment issues may impede the domain reaching exemplar status. There are significant number of vacancies and as the domain moves forward through the matrices, this will become a greater issue that is reiterated across all areas within the TI framework. |  |
| TIIF Domain addressed | - All |  |
| Issues to be referred to another Committee | - None |  |
| Matters requiring escalation to the Board: | - None |  |
| Well-being of Future Generations Act Sustainable Development Principle | Describe how the items of business and the development of any proposals considered by the Committee gave adequate consideration to the sustainable development principles or if not indicate the reasons for this. 1. Balancing short term need with long term planning for the future – covered by the strategy, planning and performance domain. 2. Working together with other partners to deliver objectives – covered by the engagement work 3. Involving those with an interest and seeking their views – covered by the engagement work; 4.Putting resources into preventing problems occurring or getting worse – via WG funding allocation; 5. Considering impact on all well-being goals together and on other bodies – covered by engagement work. |  |
| Planned business for the next meeting: | - Monitoring progress against the framework and identification of any issues. |  |
| Date of next meeting: | 25.04.22 (rescheduled to 03.05.22) |  |